## January - retainer
Page/Product name | Status | Notes | Days Adam | Days Hani
13/1/25 - Meetings and overview of upcoming roadmap |  |  | 0.2
14/1/25 - Launch darkly pre build for testimonials |  |  | 0.5
15/1/25 - Launch Darkly prep - duplicating the refinance pages and tuning the conflics for the testimonial slider |  |  | 1
16/1/25 - open graph rework |  |  | 1
21/01/25 - Launching refi experiemtn, reworking HLMS hero and card |  |  | 0.5
22/01/25 - Web clone and class audit and removal + Component audit + Page audit and archiving removal |  |  | 1
28/01/25 - Accessibility Audit to upadted 2.0 pages and lighthouse checking |  |  | 1
29/01/25 - Accessibility Audit and creation of audit spreadsheet |  |  | 1
30/01/25 - Accessibility Audit updates continuation + component creation. |  |  | 1
Total Days |  |  | 7.2
Extra days |  |  | 0
Invoiced

## February - retainer
Page/Product name | Status | Notes | Days Adam | Days Hani
6/2/25 - PDF updates / Ended up not actually being able to do it as it was an intercomm job |  |  | 0.25
7/2/25 - Launch darkly testimonials experiment launch |  |  | 0.5
10/2/25 - Code block bundle removal and embed per component update |  |  | 1
11/2/25 - V2 API replacement and updates |  |  | 1
12/2/25 - Unloan Logo files upload - V2 spinner Patch - Color accent animation check |  |  | 1
13/2/25 - Colour accent + new .json accent added. Updated code for breakpoints |  |  | 1
14/2/25 - Remove debugging markers, amend Spinner caret to be Superscript, rate drop workshop |  |  | 1
17/2/25 - Rate drop hero builds and React widget uplifts |  |  | 1
18/2/25 - Final sweep of testing for new hero sections for Rate drop - Alignment for deployment |  |  | 1
19/2/25 - Hero adjustments for Thurs night prod launch - Card uplift and component creation for accessible rates card |  |  | 1
20/2/25 - Final adjustments before launch party at 9pm |  |  | 1
21/2/25 - Post launch tweaks to spinners and rate cards on Unord landing pages |  |  | 1
24/2/25 - Accent and logo uplift check for Friday launch. PDF updates to Deceased estate forms. |  |  | 1
25/2/25 - Final accent and logo design walkthrough and approval. Spinner update for decimal point. |  |  | 1
26/2/25 - Staging check for all upcoming accent colour and logo change pages. |  |  | 1
Total Days |  |  | 13.75
Extra days |  |  | 4.8
Invoiced

## March - retainer
Page/Product name | Status | Notes | Days Adam | Days Hani
3/3/25 - Week ahead |  |  | 0.5
4/3/25 - SEO updates, Card shift + BLoom animation removal |  |  | 0.75
3/3/25 - Back to back meetings form 9am-2pm - Sprint planning and Tile uplift beginning |  |  | 1
12/3/25 - HP - experiment and CommBank tile removal projects |  |  | 1
13/3/25 - Tile uplifts and component creation meetings |  |  | 1
14/3/25 - Meeting for potential launch of initial experiment for Sprint 34, training |  |  | 1
17/3/25 - Unloan training |  |  | 1
18/3/25 - WIP and intro to Design uplift for new experiment, launch of experiment 1 for Sprint 34 |  |  | 1
19/3/25 - Devwork on Unord experiment |  |  | 1
20/3/25 - Unord Treatment pages 1 & 2 + Lottie testing for loyalty card |  |  | 1
21/3/25 - WebM movie scrollTrigger animation for loyalty card + Finalisation of Unord treatment pages |  |  | 1
22/3/25 - Unord treatment pages uplift and additional development of extra cards and Awards structure |  |  | 1
Total Days |  |  | 11.25
Extra days |  |  | 3
Invoiced
/

## April -Retainer
Page/Product name | Status | Notes | Days Adam | Days Hani
HOLIDAYS 1-13th
17/4/25 - Sprint refine and meetings. Prep for finder and Loyalty Discount page |  |  | 1
18/4/25 - Loyalty discount page and tile build |  |  | 1
21/4/25 - Loyalty page updates |  |  | 1
22/4/25 - Finder page build from design |  |  | 1
23/4/25 - Loyalty Discount spritesheet adjustments |  |  | 0.25
24/4/25 - Finder page updates, Apply now card refit, Loyalty discount card fine tuning |  |  | 1
28/4/25 - Finder page updates |  |  | 1
29/4/25 - Finder page finishing touches |  |  | 1
Total Days |  |  | 7.25
Extra days
Invoiced

## May -Retainer
Page/Product name | Status | Notes | Days Adam | Days Hani
1/5/25 - Accessibility upgrades across components |  |  | 1
2/5/25 - Sprint retro, Acquisition crew meet |  |  | 0.5
5/5/25 - Backlog refinement and discussions on upcoming RBA rate change. Website Safari issues fixup, slide animation for toggle |  |  | 1
6/5/25 - Skiplink implementation and CTA banner on calcs |  |  | 1
7/5/25 - accessibility fix on apply in six steps, Loyalty page first pass |  |  | 1
8/5/25 - Loyalty page final tweaks and updates - finder video updates and functionality code base update |  |  | 1
9/5/25 - POC for the new campaign rate animation |  |  | 1
12/5/25 - Finder page launch and monitoring + Homepage error fix + Rate spinner updates for rate reduction campaign |  |  | 1
13/5/25 - Rate cut rate-spinner animation updates |  |  | 1
14/5/25 - Rate cut rate-spinner animation, calculators kart animation, |  |  | 1
15/5/25 - Further rate cut animation scripts for buy a home and refinance |  |  | 1
19/5/25 - RBA rate cut prep, QAing |  |  | 1
20/5/25 - RBA cash-rate drop Laucnh day!! |  |  | 1
Total Days |  |  | 12.5
Extra days
Invoiced

## June -Retainer
Page/Product name | Status | Notes | Days Adam | Days Hani
2/6/25 - Early Rate Cut campaign animation hero |  |  | 1
3/6/25 - Sprint plannig and ERC animation updates + lottie sub purchase for Markus T |  |  | 1
Total Days |  |  | 2
Extra days
Invoiced

## July -Retainer
Page/Product name | Status | Notes | Days Adam | Days Hani
Total Days |  |  | 0
Extra days
Invoiced

## August - Retainer
Page/Product name | Status | Notes | Days Adam | Days Hani
Total Days |  |  | 15.5
Extra days
Invoiced

## September - Retainer
Page/Product name | Status | Notes | Days Adam | Days Hani
Total Days |  |  | 0
Extra days
Invoiced

## October - Retainer
| Status | Notes | Days Adam | Days Hani
Total Days |  |  | 0
Extra days
Invoiced

## November - Retainer
Page/Product name | Status | Notes | Days Adam | Days Hani
Total Days |  |  | 0
Extra days
Invoiced

## December - Retainer
Page/Product name | Status | Notes | Days Adam | Days Hani
Total Days |  |  | 0
Extra days
Invoiced